#oneTRL Platform   Globalvia headquarters
Contract compliance evidence pack
A23 Beira Interior
Contract year to date, January to October 2026. Issued 22 October 2026.
Demo data. Illustrative figures for nine concessions, year to date January to October 2026. Changes compare October with September. Trends, forecasts and AI predictions are generated for the demo. Do not use these figures for decisions.
Illustrative contract terms. Obligations, thresholds, deduction rates and clause references are examples, not taken from any concession contract.
Summary
Deductions so far this contract year come to €93k: €81k settled, €6k notified and open to dispute, and €6k provisional. At the rate of the last three months the year ends at €106k. 22% of the annual cap of €415k is used. 3 obligations were below threshold in October, 2 with gaps in the evidence.
By obligation
	Obligation
	Clause
	Threshold
	Measured in October
	Months below
	Deductions

	Lane availability
	Schedule 6, 2.1
	at least 99.0%
	● 99.2%
	4
	€16k

	Incident response
	Schedule 4, 3.2
	at least 85.0%
	● 87.5%
	0
	€0

	Category 1 defects
	Schedule 5, 4.1
	at least 95.0%
	● 93.4%
	10
	€47k

	Category 2 defects
	Schedule 5, 4.2
	at least 90.0%
	● 88.0%
	10
	€19k

	Safety inspections
	Schedule 5, 2.3
	at least 90.0%
	● 92.1%
	1
	€7

	Emergency phones
	Schedule 7, 1.4
	at least 98.0%
	● 97.0%
	10
	€10k

	Traveller information
	Schedule 7, 3.1
	at most 8.0 min
	● 6.8 min
	2
	€158



Lane availability (Schedule 6, 2.1)
Lanes open to traffic for at least 99.0% of scheduled lane-hours each month. Deduction: €1,500 per 0.1 point below 99.0%, scaled for network length. 4 months below threshold, €16k in total.
	Month
	Measured
	Result
	Deduction
	Settlement

	January
	98.8%
	● Missed
	€10k
	Settled

	February
	99.1%
	● Met
	€0
	

	March
	99.1%
	● Met
	€0
	

	April
	98.9%
	● Missed
	€5k
	Settled

	May
	99.0%
	● Missed
	€2k
	Settled

	June
	99.1%
	● Met
	€0
	

	July
	99.0%
	● Missed
	€730
	Settled

	August
	99.2%
	● Met
	€0
	

	September
	99.0%
	● Met
	€0
	

	October
	99.2%
	● Met
	€0
	



Incident response (Schedule 4, 3.2)
Patrol on scene within 20 minutes for at least 85% of incidents. Deduction: €600 per point below 85%, scaled for network length. 0 months below threshold, €0 in total.
	Month
	Measured
	Result
	Deduction
	Settlement

	January
	86.0%
	● Met
	€0
	

	February
	85.5%
	● Met
	€0
	

	March
	85.8%
	● Met
	€0
	

	April
	85.4%
	● Met
	€0
	

	May
	85.1%
	● Met
	€0
	

	June
	85.7%
	● Met
	€0
	

	July
	85.6%
	● Met
	€0
	

	August
	88.1%
	● Met
	€0
	

	September
	86.6%
	● Met
	€0
	

	October
	87.5%
	● Met
	€0
	



Category 1 defects (Schedule 5, 4.1)
At least 95% of category 1 defects made safe within 24 hours. Deduction: €750 per point below 95%, scaled for network length. 10 months below threshold, €47k in total.
	Month
	Measured
	Result
	Deduction
	Settlement

	January
	91.7%
	● Missed
	€6k
	Settled

	February
	92.1%
	● Missed
	€6k
	Settled

	March
	92.8%
	● Missed
	€4k
	Settled

	April
	92.5%
	● Missed
	€5k
	Settled

	May
	91.7%
	● Missed
	€6k
	Settled

	June
	93.1%
	● Missed
	€4k
	Settled

	July
	93.1%
	● Missed
	€4k
	Settled

	August
	92.3%
	● Missed
	€5k
	Settled

	September
	93.2%
	● Missed
	€4k
	Notified, open to dispute

	October
	93.4%
	● Missed
	€3k
	Provisional



Category 2 defects (Schedule 5, 4.2)
At least 90% of category 2 defects repaired within 7 days. Deduction: €400 per point below 90%, scaled for network length. 10 months below threshold, €19k in total.
	Month
	Measured
	Result
	Deduction
	Settlement

	January
	87.4%
	● Missed
	€3k
	Settled

	February
	88.7%
	● Missed
	€1k
	Settled

	March
	88.5%
	● Missed
	€2k
	Settled

	April
	87.3%
	● Missed
	€3k
	Settled

	May
	88.0%
	● Missed
	€2k
	Settled

	June
	88.7%
	● Missed
	€1k
	Settled

	July
	87.1%
	● Missed
	€3k
	Settled

	August
	88.7%
	● Missed
	€1k
	Settled

	September
	89.0%
	● Missed
	€1k
	Notified, open to dispute

	October
	88.0%
	● Missed
	€2k
	Provisional



Safety inspections (Schedule 5, 2.3)
At least 90% of scheduled safety inspections completed on time. Deduction: €250 per point below 90%, scaled for network length. 1 month below threshold, €7 in total.
	Month
	Measured
	Result
	Deduction
	Settlement

	January
	90.1%
	● Met
	€0
	

	February
	91.2%
	● Met
	€0
	

	March
	90.0%
	● Missed
	€7
	Settled

	April
	91.6%
	● Met
	€0
	

	May
	91.2%
	● Met
	€0
	

	June
	91.3%
	● Met
	€0
	

	July
	92.0%
	● Met
	€0
	

	August
	90.9%
	● Met
	€0
	

	September
	93.0%
	● Met
	€0
	

	October
	92.1%
	● Met
	€0
	



Emergency phones (Schedule 7, 1.4)
SOS points working at least 98% of the time. Deduction: €500 per point below 98%, scaled for network length. 10 months below threshold, €10k in total.
	Month
	Measured
	Result
	Deduction
	Settlement

	January
	97.7%
	● Missed
	€365
	Settled

	February
	97.6%
	● Missed
	€565
	Settled

	March
	97.2%
	● Missed
	€1k
	Settled

	April
	97.3%
	● Missed
	€867
	Settled

	May
	97.1%
	● Missed
	€1k
	Settled

	June
	97.2%
	● Missed
	€1k
	Settled

	July
	96.8%
	● Missed
	€2k
	Settled

	August
	97.3%
	● Missed
	€868
	Settled

	September
	97.1%
	● Missed
	€1k
	Notified, open to dispute

	October
	97.0%
	● Missed
	€1k
	Provisional



Traveller information (Schedule 7, 3.1)
Closures shown on message signs within 8 minutes (monthly median). Deduction: €400 per minute over 8 minutes, scaled for network length. 2 months below threshold, €158 in total.
	Month
	Measured
	Result
	Deduction
	Settlement

	January
	8.0 min
	● Missed
	€46
	Settled

	February
	7.2 min
	● Met
	€0
	

	March
	8.1 min
	● Missed
	€112
	Settled

	April
	6.8 min
	● Met
	€0
	

	May
	6.8 min
	● Met
	€0
	

	June
	7.6 min
	● Met
	€0
	

	July
	6.6 min
	● Met
	€0
	

	August
	7.2 min
	● Met
	€0
	

	September
	6.6 min
	● Met
	€0
	

	October
	6.8 min
	● Met
	€0
	



Evidence for October
1. Category 1 defects: 5 records missing (at least 95.0% required). Collect before the deduction is notified.
1. Category 2 defects: 6 records missing (at least 90.0% required). Collect before the deduction is notified.
How deductions are calculated
1. Each obligation is assessed monthly against its threshold. A month below threshold costs the rate for each point (or minute) of shortfall.
1. Rates are for a concession of average network length and scale with each concession’s length.
1. Deductions stop once a concession reaches its annual cap. Amounts above the cap are recorded but not charged.
1. September’s deductions have been notified and can be disputed; October’s are provisional until assessment.
1. Concessions covered: A23 Beira Interior.
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