# Contract compliance evidence pack

M50

Contract year to date, January to October 2026. Issued 22 October 2026.

Demo data. Illustrative figures for nine concessions, year to date January to October 2026. Changes compare October with September. Trends, forecasts and AI predictions are generated for the demo. Do not use these figures for decisions.

Illustrative contract terms. Obligations, thresholds, deduction rates and clause references are examples, not taken from any concession contract.

## Summary

Deductions so far this contract year come to €3k: €3k settled, €33 notified and open to dispute, and €0 provisional. At the rate of the last three months the year ends at €3k. 3% of the annual cap of €102k is used. 0 obligations were below threshold in October, 0 with gaps in the evidence.

## By obligation

| Obligation | Clause | Threshold | Measured in October | Months below | Deductions |
| --- | --- | --- | --- | --- | --- |
| Lane availability | Schedule 6, 2.1 | at least 99.0% | ● 99.1% | 3 | €2k |
| Incident response | Schedule 4, 3.2 | at least 85.0% | ● 92.8% | 0 | €0 |
| Category 1 defects | Schedule 5, 4.1 | at least 95.0% | ● 96.2% | 2 | €402 |
| Category 2 defects | Schedule 5, 4.2 | at least 90.0% | ● 93.2% | 0 | €0 |
| Safety inspections | Schedule 5, 2.3 | at least 90.0% | ● 95.5% | 0 | €0 |
| Emergency phones | Schedule 7, 1.4 | at least 98.0% | ● 98.3% | 6 | €364 |
| Traveller information | Schedule 7, 3.1 | at most 8.0 min | ● 5.4 min | 0 | €0 |

## Lane availability (Schedule 6, 2.1)

Lanes open to traffic for at least 99.0% of scheduled lane-hours each month. Deduction: €1,500 per 0.1 point below 99.0%, scaled for network length. 3 months below threshold, €2k in total.

| Month | Measured | Result | Deduction | Settlement |
| --- | --- | --- | --- | --- |
| January | 98.9% | ● Missed | €977 | Settled |
| February | 99.0% | ● Met | €0 |  |
| March | 99.1% | ● Met | €0 |  |
| April | 99.1% | ● Met | €0 |  |
| May | 98.9% | ● Missed | €589 | Settled |
| June | 99.1% | ● Met | €0 |  |
| July | 99.2% | ● Met | €0 |  |
| August | 98.9% | ● Missed | €535 | Settled |
| September | 99.0% | ● Met | €0 |  |
| October | 99.1% | ● Met | €0 |  |

## Incident response (Schedule 4, 3.2)

Patrol on scene within 20 minutes for at least 85% of incidents. Deduction: €600 per point below 85%, scaled for network length. 0 months below threshold, €0 in total.

| Month | Measured | Result | Deduction | Settlement |
| --- | --- | --- | --- | --- |
| January | 90.9% | ● Met | €0 |  |
| February | 93.0% | ● Met | €0 |  |
| March | 91.8% | ● Met | €0 |  |
| April | 92.6% | ● Met | €0 |  |
| May | 93.3% | ● Met | €0 |  |
| June | 91.9% | ● Met | €0 |  |
| July | 91.3% | ● Met | €0 |  |
| August | 92.0% | ● Met | €0 |  |
| September | 92.0% | ● Met | €0 |  |
| October | 92.8% | ● Met | €0 |  |

## Category 1 defects (Schedule 5, 4.1)

At least 95% of category 1 defects made safe within 24 hours. Deduction: €750 per point below 95%, scaled for network length. 2 months below threshold, €402 in total.

| Month | Measured | Result | Deduction | Settlement |
| --- | --- | --- | --- | --- |
| January | 94.5% | ● Missed | €216 | Settled |
| February | 96.3% | ● Met | €0 |  |
| March | 94.6% | ● Missed | €186 | Settled |
| April | 96.1% | ● Met | €0 |  |
| May | 95.2% | ● Met | €0 |  |
| June | 96.5% | ● Met | €0 |  |
| July | 96.7% | ● Met | €0 |  |
| August | 96.2% | ● Met | €0 |  |
| September | 95.7% | ● Met | €0 |  |
| October | 96.2% | ● Met | €0 |  |

## Category 2 defects (Schedule 5, 4.2)

At least 90% of category 2 defects repaired within 7 days. Deduction: €400 per point below 90%, scaled for network length. 0 months below threshold, €0 in total.

| Month | Measured | Result | Deduction | Settlement |
| --- | --- | --- | --- | --- |
| January | 95.9% | ● Met | €0 |  |
| February | 94.7% | ● Met | €0 |  |
| March | 95.6% | ● Met | €0 |  |
| April | 94.4% | ● Met | €0 |  |
| May | 94.5% | ● Met | €0 |  |
| June | 94.0% | ● Met | €0 |  |
| July | 94.1% | ● Met | €0 |  |
| August | 92.8% | ● Met | €0 |  |
| September | 93.7% | ● Met | €0 |  |
| October | 93.2% | ● Met | €0 |  |

## Safety inspections (Schedule 5, 2.3)

At least 90% of scheduled safety inspections completed on time. Deduction: €250 per point below 90%, scaled for network length. 0 months below threshold, €0 in total.

| Month | Measured | Result | Deduction | Settlement |
| --- | --- | --- | --- | --- |
| January | 95.0% | ● Met | €0 |  |
| February | 95.5% | ● Met | €0 |  |
| March | 96.3% | ● Met | €0 |  |
| April | 95.6% | ● Met | €0 |  |
| May | 96.8% | ● Met | €0 |  |
| June | 95.8% | ● Met | €0 |  |
| July | 95.9% | ● Met | €0 |  |
| August | 95.4% | ● Met | €0 |  |
| September | 95.1% | ● Met | €0 |  |
| October | 95.5% | ● Met | €0 |  |

## Emergency phones (Schedule 7, 1.4)

SOS points working at least 98% of the time. Deduction: €500 per point below 98%, scaled for network length. 6 months below threshold, €364 in total.

| Month | Measured | Result | Deduction | Settlement |
| --- | --- | --- | --- | --- |
| January | 97.4% | ● Missed | €192 | Settled |
| February | 97.7% | ● Missed | €86 | Settled |
| March | 97.9% | ● Missed | €28 | Settled |
| April | 98.2% | ● Met | €0 |  |
| May | 97.9% | ● Missed | €20 | Settled |
| June | 98.2% | ● Met | €0 |  |
| July | 98.4% | ● Met | €0 |  |
| August | 98.0% | ● Missed | €5 | Settled |
| September | 97.9% | ● Missed | €33 | Notified, open to dispute |
| October | 98.3% | ● Met | €0 |  |

## Traveller information (Schedule 7, 3.1)

Closures shown on message signs within 8 minutes (monthly median). Deduction: €400 per minute over 8 minutes, scaled for network length. 0 months below threshold, €0 in total.

| Month | Measured | Result | Deduction | Settlement |
| --- | --- | --- | --- | --- |
| January | 6.1 min | ● Met | €0 |  |
| February | 5.9 min | ● Met | €0 |  |
| March | 5.5 min | ● Met | €0 |  |
| April | 6.3 min | ● Met | €0 |  |
| May | 6.0 min | ● Met | €0 |  |
| June | 6.2 min | ● Met | €0 |  |
| July | 5.6 min | ● Met | €0 |  |
| August | 5.9 min | ● Met | €0 |  |
| September | 5.9 min | ● Met | €0 |  |
| October | 5.4 min | ● Met | €0 |  |

## Evidence for October

Evidence is complete for every obligation in October.

## How deductions are calculated

- Each obligation is assessed monthly against its threshold. A month below threshold costs the rate for each point (or minute) of shortfall.

- Rates are for a concession of average network length and scale with each concession’s length.

- Deductions stop once a concession reaches its annual cap. Amounts above the cap are recorded but not charged.

- September’s deductions have been notified and can be disputed; October’s are provisional until assessment.

- Concessions covered: M50.